**MR Imaging Teleconference Minutes 03/17/2020**

ATRI Moving Meetings to virtual for foreseeable future.

Mayo has moved to virtual meetings as well.

**1.      Review Minutes from the February Call (Below)**

Noted, no changes recommended. 

**2.      MRI Analysis Processing Report – Update missing data for all labs - Subject ID and Date (Harvey)**

a.       All analysis labs should have received an email from Danielle with spreadsheets that contain analysis updates/missing data for their lab.

b.      Reminder – All sites should be current with analysis by April 1, to allow time for compiling data to present at May 4th Steering Committee Meeting

c.       DEADLINE - 2 Slides from each lab outlining an analysis they’ve done with ADNI 3 data by April 20.

Updated ADNI2 report not sent, Naomi working on missing QC lists for ADNI3.

Reiterated that the ADNI Steering committee meeting is still going as planned (virtual)

Timelines have not changed, would still like all analysis groups to send as much data as possible in by April 1st.

Reminder that Dr. Jack needs two slides by April 20th from each analysis group.

**3.      DTI Harmonization Presentation (Thompson)**

*Postponed until April*

Noted, Dr. Thompson will plan to review in April.

**4.      Update on ADNI Philips Advanced protocol**

a.       DTI will change from 1-3 shells

b.      ASL moves from 2D PASL to 3D pCASL

c.       Move to 3TE Axial GRE

d.      fMRI Will continue as is.

                                                              i.      Working with Philips to compile and will send out as soon as possible.

Noted.

Dr. Jack — Site qualification hopefully will not be effected by Covid 19 virus, but we may see a decline or stoppage of research MRI scanning for a period of time.

**5.      Update on Face De-Identification (Schwarz/Jack)**

Discussed on the last call, Dr. Jack feels how ADNI proceeds will be driven by the consensus views of the Steering Committee and PPSB.

Dr. Schwarz continues to work on making the defacing better as face recognition software continues to get better.

**6.       Updated outline of ADNI history and MR heterogeneity (Gunter)**

Noted, will continue to work on moving forward.  

**7.      Next Call 4/21/2020 --** Noted.